2021 PROGRESS REPORT

Quarter: (circle one)			2021 1st

Grant Program, Number and Title: Pollinator RCN RCN GSA 00096

Organization: Poulos Environmental Consulting

Project Leader:  Poulos

Abstract: Please provide a short (1-2 paragraphs) abstract that addresses EACH of the following: the objectives of your project, accomplishments to date, future plans and timelines with an estimate for when the project will be completed.

During this quarter, we worked with site managers to get them to send us their missing Pollinator RCN data from all years. Upon receiving the data, we have worked to key the data into the master vegetation database for the project. We have completed all data entry for all sites for which we received data. We are now reaching out to the final missing sites to make sure that we’ve keyed in all vegetation data that exists for the project.

Were planned goals/objectives achieved last quarter?

Yes

Progress Achieved: (For each Goal/Objective, list Planned and Actual Accomplishments)

All vegetation data have been keyed in.

Difficulties Encountered: Some sites are still missing data or did not collect 2019 or 2020 data.

# Activities Anticipated Next Quarter:  Finish vegetation data aggregation and vegetation database construction.

Expected End Date: May 30, 2021

Costs:

Total life to date expenses (include this quarter): $23,795

Total Approved Budgeted Funds: $29.330

Are you within the approved budget plan and categories? yes

Signature:

Date:  03/17/21