2022 PROGRESS REPORT

Quarter: (circle one)		2022 1st	2022 2nd	2022 3rd	2022 4th

Grant Program, Number and Title: RCN 2 Project 2 Job1 GSA 00133  Nocturnal moth surveying, specimen identification and data management

Organization: Lloyd Center for the Environment

Project Leader:  Mark J. Mello

Abstract: Please provide a short (1-2 paragraphs) abstract that addresses EACH of the following: the objectives of your project, accomplishments to date, future plans and timelines with an estimate for when the project will be completed.

Nineteen field trips have been conducted during May through September (Albany pine bush-5; Katama 5; Nantucket-4; Nicholas/Pratt Farms, RI 5). I travelled to Nantucket for the first trip in order to train staff at the Nantucket Conservation Foundation and Linda Loring Nature Foundation  who conducted the trapping and sent the moth samples to me on the Seastreak Ferry to New Bedford, This eliminated the situation last year when booking the ferry had to be made months in advance, resulting in two field samples at Head of the Plains being aborted due to storms. I provided all equipment and the sampling window dates so that they could trap on appropriate nights within the window.

All macro-moths and selected micro-moths from these samples have been sorted, and counted; and vouchers saved and spread. All appropriate field data (temperature, humidity, vegetation, weather conditions has been recorded, and data entered on Excel spreadsheets.

Progress Achieved: (For each Goal/Objective, list Planned and Actual Accomplishments)

The nineteen field trips have produced 6,351 macro-moths and targeted micro-moths (6 Families)  comprising 418 species of which 655 were saved as vouchers. All have been pinned and/or spread. Data entry as per agreed upon format is complete for macro-moths through September.. Selected, but not necessarily comprehensive set of individuals of other micro-moths totaling 192 individuals were saved and pinned. An additional 219 micro-moths await identification. Vegetation data comprised of recording the top five species at each site is complete through September.

Difficulties Encountered: In addition to those mentioned in previous progress report, the last field trip to Nantucket that I had planned for the end of September has been delayed until October due to a combination of adverse weather and my testing positive for Covid. The folks who conducted the summer trapping agreed to do the October sampling, which took place on October 12 (Linda Loring Nature Foundation) and October 16 (Head of the Plains). Thsese samples will be processed next week, as this past week I had Covid , but am okay now.

# Activities Anticipated Next Quarter:

In addition to the final Nantucket field trip, the final data spreadsheets will be completed by the end of October and sent to Elizabeth Cristfield. A narrative report will be produced in November. Voucher specimens will be delivered to University in December and final bill submitted.

Expected End Date:  December 31, 2022

Costs:

Total life to date expenses: $27,217.74

Total Approved Budgeted Funds: $32,500

Are you within the approved budget plan and categories? Yes, remaining expenses estimated to be about $2,000.00

Signature:

Date:  October 13, 2022