2021 PROGRESS REPORT

Quarter: (circle one)		2021 1st	2021 2nd	2021 3rd	2021 4th

Grant Program, Number and Title: Regional Conservation Needs (RCN) Project “Habitat for Pollinators: Improving Management for Regionally Significant Xeric Grasslands, Barrens, and Woodlands in the Northeast”

Organization: Northeast Association of Fish & Wildlife Agencies

Project Leader:  John Heilferty

Abstract: Please provide a short (1-2 paragraphs) abstract that addresses EACH of the following: the objectives of your project, accomplishments to date, future plans and timelines with an estimate for when the project will be completed.

The primary objective of the RCN Project is to improve the ability of northeast states to implement cost-effective habitat management for the benefit of native pollinators and Regional Species of Greatest Conservation Need (RSGCN) that depend upon these priority habitat types.

Accomplishments to date include the following:

- Sampling effort #1 (April), #2 (May), and #3 (June) at all three contracted sites – Concord, NH., Wells, ME, and Kennebunk, ME

- Processed all specimens collected – sorted, identified, mounted (pinned) and labeled, entered into db

- Visited UNH IMNvertebrate Museum and coordinated on submission protocols for vouchers

- Submitted macro-moth specimens for Concord collection to date to UNH Invertebrate Museum; collections for Maine pending transport to Orono

- Sent all micro-moth collections to Jason Dombrowskie at Cornell

- Completed floral resources tally at all three sites, and entered data in db

- Completed first of two soil penetrometer readings for bee bowl transects at all three sites

- Updated GIS data layers for all sites

Next sampling periods to be completed: August, September-October 2021, plus the same or similar effort (TBD) in 2022; completion date no later than December 31, 2022

Were planned goals/objectives achieved last quarter? Yes

Progress Achieved: (For each Goal/Objective, list Planned and Actual Accomplishments)

(see above)

Difficulties Encountered: Weather in April did not follow predictions and was not optimal for maximum species counts in both Wells and Kennebunk; numbers of beetles attracted to blacklight traps in June ended up damaging many micro specimens; weather change in June at Kennebunk prevented many collections

# Activities Anticipated Next Quarter:  Sampling efforts x 2, vouchers submitted, collection data entered and processed

Expected End Date: December 31, 2022

Costs:

Total life to date expenses (include this quarter):

| Date | Item | Sub-Total | Match Amt. (35%) | Net Due |
| --- | --- | --- | --- | --- |
| April 2021 | $1077 ea. x 3 for Concord, Wells, Kennebunk | 3231.00 | 1130.85 | $2100.15 |
|  | Mileage – 469 miles @ $.56/mile | 262.64 | 91.92 | $170.72 |
|  | $1.55 per specimen recorded x 139 | 215.45 | 75.41 | $140.04 |
| May 2021 | $1077 ea. x 3 for Concord, Wells, Kennebunk | 3231.00 | 1130.85 | $2100.15 |
|  | Mileage – 478 miles @ $.56/mile | 267.68 | 93.69 | $173.99 |
|  | $1.55 per specimen recorded x 953 | 1477.15 | 517.00 | $960.15 |
| June 2021 | $1077 ea. x 3 for Concord, Wells, Kennebunk | 3231.00 | 1130.85 | $2100.15 |
|  | Mileage – 401 miles @ $.56/mile | 224.56 | 78.60 | $145.96 |
|  | $1.55 per specimen recorded x 1477 | 2289.35 | 801.27 | $1488.08 |
| July 30, 2021 | TOTAL | 14,429.83 | 5050.44 | $9379.39 |

Are you within the approved budget plan and categories? Yes

Signature:

Date:  July 30, 2021