2020 PROGRESS REPORT

Quarter: (circle one)		2020 1st	2020 2nd	2020 3rd	2020 4th

Grant Program, Number and Title: RCN, GSA 00045, Assessment of Spotted Turtles in New York

Organization: SUNY Potsdam Research Foundation

Project Leader:  Glenn Johnson

Abstract: Please provide a short (1-2 paragraphs) abstract that addresses EACH of the following: the objectives of your project, accomplishments to date, future plans and timelines with an estimate for when the project will be completed.

The overarching objective of this RCN project is to support the strategic implementation of regional conservation planning for at-risk turtles in the Northeastern States, addressing the most time-sensitive research and management needs for at least five priority species (Blanding’s, Eastern Box, Wood, Spotted Turtles, and Northern Diamondback Terrapins) through four separate but complementary initiatives.

SUNY Potsdam has specific tasks to contribute toward this overarching objective for Spotted Turtles.  These are:

- Coordinate selection of study areas with the State, and permissions and permits that will be required.  This component of the project has been completed for sites to sample in 2020.

- Conduct Trap Rapid Assessments (TRA), Demographic Assessments (DA) or Visual Rapid Assessments (VRA) surveys for spotted turtles at 10 – 15 sites.  This task was for 2019 completed in the 2nd quarter. This task was for 2020 completed in the 3rd quarter.

- Collect DNA samples of each individual spotted turtle encountered.  This task for 2019 was completed in the 2nd quarter. This task was for 2020 completed in the 3rd quarter.

Future plans. All field work (trapping and blood sampling) for this project was completed in August 2020. A  final report will be prepared by January 2021.

Were planned goals/objectives achieved last quarter? Yes

Progress Achieved: (For each Goal/Objective, list Planned and Actual Accomplishments)

1.Selection of study areas

Identification of possible survey sites was initiated by searching the New York State Amphibian and Reptile Atlas records and consultation with regional experts on this species.  Selection was completed using a combination of ArcGIS and Google Earth followed by field visits. After identifying a potential site an attempt was made to contact the landowner. Not all sites identified were surveyed owing to a lack of permission. Wetlands were on a combination of state and privately owned lands. A single day at the start of a new trap period was set aside for reconnoitering possible wetlands. The assessment was made by first inspecting the wetland by air using a drone and then following up on the most promising wetlands on foot. Two determining factors for site suitability were the presence of narrow channels in the wetland and the verification of sufficient water depth to allow deployment of Promar traps. After deciding on potential reference sites with the overall site as well as trap number and placement, personnel were dispatched to conduct trapping on the following day using the protocol developed by the Spotted Turtle Working Group.

Sixteen sites were selected for initial assessment as potential survey sites, eight of which had evidence of spotted turtle presence.  Of these, 11 were assessed in 2019, 4 were assessed earlier in 2020 and four were assessed this quarter; permission was granted for all and all were sampled with trapping events.  Three of the 4 new sites this quarter were in northeastern New York.

2. Conduct Trap Rapid Assessments (TRA), No Demographic Assessments (DA) this quarter

Trap Rapid Assessment Results

NY-WA-DB

- 7/6/2020 – 7/10/2020

- 4 full references deployed

- 1 spotted turtle captured and tissue sample taken

NY-SA-WI

- 7/6/2020 – 7/10/2020

- 4 references deployed

- No spotted turtles detected

NY-ES-BR

- 7/12/2020 – 7/20/2020

- 5 references deployed, 3 had only 3 traps

- No spotted turtles detected

- Water levels very low

NY-JE-CF

- 7/19/2020 – 7/23/2020

- 4 full references deployed

- No spotted turtles detected

Summary – A total of 1 (one) unique spotted turtle weas captured this quarter and tissue samples were taken from it.

3. Collect DNA samples

Over all sites, 89 genetic (blood) samples were obtained over 2 field seasons, including 1 this quarter. There were only 2 sites where over 20+ samples were obtained, both in 2019.

Difficulties Encountered:

- Some difficulty setting and checking traps by one person at several hard-to access sites

- Collecting very subjective habitat data i.e. percent underwater vegetation

- Water levels were unusually low this field season and was very noticeable at the especially at the NY-ES-BR and NY-SA-WI

- For some sites, there were delays in obtaining permission to access, but we were not denied at any site so far.

# Activities Anticipated Next Quarter:  Completion of all field sampling.  Begin data entry and preparation of final report.  All genetic samples collected to date were sent to Rodney Dyer’s lab and were received on 10/6/2020.

Expected End Date:  November 2020

Costs:

Total life to date expenses (include this quarter): $22,322.12

Total Approved Budgeted Funds: $23,333.00

Are you within the approved budget plan and categories? Yes

Signature:

Date:  10 October 2020