NORTHEAST REGIONAL CONSERVATION NEEDS GRANT

2017 PROGRESS REPORT

Quarter: 		2017 2nd

Grant Program, Number and Title:

RCN 2016-06 Assessing Land Snails in the Northeast

Organization:

Appalachian Conservation Biology

Project Leader:

Kenneth P. Hotopp

Abstract:

In the second quarter of 2017 we completed initial county occurrence maps of the region’s 300-plus land snail species, which will be incorporated into species profiles. Species profiles were written and edited for 29 of 75 species to be newly-added. Web pages were built for these new species and restructuring of the website continued.

We obtained collection permits from six states and 12 landowners/managers to date (not all states require a statewide collection permit). Field teams collected snails in parts of four states (MD, WV, PA, CT).

Were planned goals/objectives achieved last quarter?

Yes

Progress Achieved: (For each Goal/Objective, list Planned and Actual Accomplishments)

Species range maps – initial versions completed.

Restructuring website – in progress.

New species profiles – in progress, 29 completed.

Land snail field inventory – begun.

Difficulties Encountered:

Unexpected health issue may lead to future reduction in project scope.

# Activities Anticipated Next Quarter:

Continue writing new species profiles and adding these to website, begin revising/updating existing species profiles, begin writing new ecology content. Complete field inventory, begin sample sorting and identifications.

Expected End Date:

Dec. 2017

Costs:

Total life to date expenses (include this quarter):

$14,639

Total Approved Budgeted Funds:

$63,423

Are you within the approved budget plan and categories?

Yes

Signature:  Kenneth P. Hotopp

Date:  8/14/2017